## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 141
|  | Days In Sprint: |  |  |  | 3
Burndown Chart
User Stories |  | Days (Points Completed) | [9 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Task Balance | Percentage Completed
Admin-Kurssuche | 13 | Days (Points Completed) 1: 4; Days (Points Completed) 2: 9; Days (Points Completed) 3: 0 | 0 | 100%
Admin-Usersuche | 13 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 5; Days (Points Completed) 3: 8 | 0 | 100%
Admin-User anzeigen, bearbeiten | 34 | Days (Points Completed) 1: 1.8889; Days (Points Completed) 2: 10; Days (Points Completed) 3: 22 | 0.11111 | 99.67%
User-Kind anmelden | 34 | Days (Points Completed) 1: 34; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0 | 0 | 100%
Admin-Teilnehmer anzeigen, entfernen | 34 | Days (Points Completed) 1: 25.5; Days (Points Completed) 2: 8; Days (Points Completed) 3: 0 | 0.5 | 100%
User-Warenkorb | 13 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 5; Days (Points Completed) 3: 8 | 0 | 100%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 141 | 75.6111 | 38.6111 | 0.61111 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.61111 | 99.57%
Ideal Trend | 141 | 94 | 47 | 0 | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days