## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 110
|  | Days In Sprint: |  |  |  | 3
Burndown Chart
User Stories |  | Days (Points Completed) | [9 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Task Balance | Percentage Completed
Admin-Kursverwaltung | 34 | Days (Points Completed) 1: 4.5333; Days (Points Completed) 2: 22.6667; Days (Points Completed) 3: 6.9 | -0.1 | 100.3%
Admin-Kursauflösung | 13 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 3; Days (Points Completed) 3: 10 | 0 | 100%
Admin-Einstellungsverwaltung | 21 | Days (Points Completed) 1: 6.4615; Days (Points Completed) 2: 12.3529; Days (Points Completed) 3: 2.22 | -0.03448 | 100.2%
Admin-NotAllowedPeople | 21 | Days (Points Completed) 1: 7; Days (Points Completed) 2: 14; Days (Points Completed) 3: 0 | 0 | 100%
User-Datenverwaltung | 21 | Days (Points Completed) 1: 15; Days (Points Completed) 2: 5.3571; Days (Points Completed) 3: 0.6444 | -0.0015429 | 100%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 110 | 77.0051 | 19.6284 | -0.13602 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -0.13602 | 100.1%
Ideal Trend | 110 | 73.3333 | 36.6667 | 1.4211e-14 | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days